## Slide 1: Project Aurora: Enterprise Customer Data Platform
Meridian Financial Group
Mid-market commercial lender — 2,200 employees, 14 regional offices
Proposal: Unified customer data platform to replace fragmented CRM systems, spreadsheets, and legacy data warehouse

## Slide 2: Current State
Customer information spread across legacy CRM, individual spreadsheets, and a 10-year-old data warehouse with nightly batch loads
Relationship managers spend ~30% of their week gathering client info from different systems before meetings
Commercial lending team has no visibility into which clients hold treasury management or insurance products
Regulatory examiners flagged fragmented data environment for KYC and BSA/AML compliance exposure

## Slide 3: Revenue & Productivity Impact
Recovered productivity equivalent to ~40 FTEs at $95K avg loaded cost = $3.8M annually
18% of commercial clients are candidates for at least one additional product line (based on 3-branch pilot)
Estimated $12M in incremental annual revenue from cross-selling at current conversion rates
Addresses regulatory finding that could result in enforcement action if unresolved

## Slide 4: Implementation Plan
Phase 1: Data ingestion & normalization (5 months)
Phase 2: Analytics layer & API development (5 months)
Phase 3: Front-end integration with existing tools (4-8 months)
Total timeline: 14-18 months | Total budget: $4.2M (incl. $1.8M external consulting)

## Slide 5: Technical Landscape & Dependencies
Cloud architecture (Snowflake or Databricks) on existing AWS infrastructure
Team has moderate cloud experience — migrated website and mobile app to AWS 2 years ago, but nothing at this data complexity
Key dependency: Core system upgrade must complete (Q3) before Phase 2 can begin
Need to hire 2 senior data engineers + 1 data architect — similar searches have taken 3-4 months locally

## Slide 6: Growth Potential & Adjacent Use Cases
Credit risk team wants predictive models for early default detection — requires same unified data
Marketing wants real-time, event-driven outreach instead of batch campaigns
Each adjacent use case: $300K-$500K incremental investment on top of existing platform
Template for integrating 2 planned acquisitions — could compress integration from 12-18 months to 4-6 months at half the cost

## Slide 7: Operating Leverage
Ongoing support: ~3 FTEs (data engineer, analyst, platform admin)
Fixed cost remains stable whether serving 14 branches or 30
Economics become increasingly favorable as the bank grows organically or through acquisition

## Slide 8: Organizational Readiness
Strong executive sponsorship from COO — dedicated budget outside normal IT capital cycle
CTO supportive but concerned about competing priorities (core upgrade, cybersecurity remediation)
Frontline adoption risk: RMs have built personal workflows around current systems; past rollouts met resistance
Phased rollout with embedded change management, starting with 3 enthusiastic pilot branches

## Slide 9: Open Items
No formal data stewardship program — data ownership, quality standards, and access controls need resolution early
Compliance team volunteered to co-lead governance workstream
Project sponsor proposes starting recruitment before formal approval to mitigate hiring timeline risk